CONTEXTSWITCH

Parallel Execution Plan  —  3-Person Team

7-Day Sprint  |  3 Parallel Tracks  |  May 2025

| Person 1 Capture Layer 1-2 Days Work | Person 2 Intelligence Layer 4-5 Days Work | Person 3 Product Layer 4-5 Days Work |
| --- | --- | --- |

# 1. Executive Summary

ContextSwitch ka kaam 7 din mein 3 parallel tracks mein complete kiya ja sakta hai. Teeno log zyaadatar independently kaam kar sakte hain — sirf 3 critical handoff points hain jahan coordination zaruri hai.

| Total Duration | Team Size | Sync Points | Blocking Deps |
| --- | --- | --- | --- |
| 7 Days | 3 People | 3 Points | 1 Only |

KEY INSIGHT: Sirf ek hard dependency hai — Person 2 ka db.ts schema update (Day 1 end tak) done hona chahiye taaki Person 3 ka session work Day 2 se shuru ho sake. Baaki sab parallel chal sakta hai. Person 1 ka kaam 2 din mein wrap ho jata hai, phir wo testing + review mein help kar sakta hai.

# 2. 7-Day Gantt Chart (Parallel Tracks)

Har row ek task hai. Color = kaun kar raha hai. Overlap = parallel execution.

| Team / Task | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 |
| --- | --- | --- | --- | --- | --- | --- | --- |

| P1: DB Schema | Build | Done ✓ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| P1: server.ts | Routes | Done ✓ |  |  |  |  |  |
| P1: wsServer+ext |  | Events | Done ✓ |  |  |  |  |
| P1: Review/Test |  |  |  | Test | Test | Integ | Final |
| P2: aiService.ts | Setup | Claude | Done ✓ |  |  |  |  |
| P2: memoryService |  | CRUD | Query | Done ✓ |  |  |  |
| P2: stalenessService |  |  | Score | Done ✓ |  |  |  |
| P2: context enhanced |  |  |  | Merge | Done ✓ |  |  |
| P3: sessionService |  | Start | Logic | Done ✓ |  |  |  |
| P3: dashboard API |  |  | Routes | Stats | Done ✓ |  |  |
| P3: Dashboard UI |  |  | HTML | Charts | Polish | Done ✓ |  |
| P3: reconstruct API |  |  |  |  | AI call | Done ✓ |  |
| ALL: Integration |  |  |  |  |  | Sync | Final |

| ■ Person 1 (Blue) | ■ Person 2 (Green) | ■ Person 3 (Orange) | ■ All 3 Sync | ✓ = Task Complete | null = Not Working |
| --- | --- | --- | --- | --- | --- |

# 3. Person-wise Detailed Work Plan

👤 Person 1 — Capture Layer Files: db.ts, server.ts, wsServer.ts, extension.ts ¦ Est: 2 Days Active, 5 Days Review

## 3.1  Person 1 — Day-by-Day Tasks

### Day 1 — Database Foundation (MOST CRITICAL)

Yeh sabse important kaam hai. Saari team is par depend karti hai.

- db.ts kholo — existing events + braindumps tables samjho

- 3 naye tables add karo ek saath:

- sessions (id, project, start_ts, end_ts, summary, status)

- memory_nodes (id, session_id, content, type, score, project, ts)

- staleness_scores (filePath PRIMARY KEY, last_seen, edit_count, score)

- server.ts mein placeholder routes mount karo for new modules

- Test: npm run dev chala ke health check verify karo

- End of Day 1: db.ts changes Person 2 aur Person 3 ko share karo (git push)

⚠ BLOCKER: Person 3 ka sessionService.ts kaam Day 2 se shuru nahi ho sakta jab tak db.ts mein sessions table na ho. Person 1 ko Day 1 end tak yeh zaroor complete karna hai.

### Day 2-3 — WebSocket & Extension Enhancement

- wsServer.ts: terminal:log aur git:commit event types handle karo

- wsServer.ts: jab file:change aaye toh staleness_scores table bhi update karo

- extension.ts: terminal output capture add karo (onDidChangeTerminalState)

- extension.ts: git commit hooks bhi capture karo (simple exec git log -1)

- Test: VS Code mein extension chala ke saare event types verify karo

### Day 4-7 — Testing & Integration Support

- Person 2 aur Person 3 ke APIs test karo jaise ready hote jaayein

- End-to-end flow test: Extension file change → WS → DB → /context/enhanced

- Bug fixes aur performance issues

👤 Person 2 — Intelligence Layer Files: aiService.ts, memoryService.ts, stalenessService.ts, context.routes.ts ¦ Est: 5 Days

## 3.2  Person 2 — Day-by-Day Tasks

### Day 1 — Setup & AI Connection

- npm install @anthropic-ai/sdk

- .env file banao: ANTHROPIC_API_KEY=sk-ant-xxxx

- aiService.ts create karo — basic structure

- Claude API connection test karo — simple 'hello' message bhejo

- generateContextSummary() function ka skeleton likho

- Agar Claude API key nahi hai, OpenAI se shuru karo (same pattern)

Note: Person 1 ka db.ts Day 1 end tak ready ho jayega. Tum apna aiService.ts independently shuru kar sakte ho — DB ki zarurat Day 2 se hogi.

### Day 2-3 — Memory & Context Services

- memoryService.ts create karo (ab db.ts available hai — git pull karo)

- saveMemoryNode(content, type, project, sessionId) implement karo

- queryMemory(project, limit) implement karo

- buildContextFromMemory(project) implement karo — AI ke liye string banata hai

- stalenessService.ts create karo

- updateScore(filePath) implement karo — wsServer call karega

- getAllScores() implement karo — sorted by score ascending (most stale first)

### Day 4 — Context Route Enhancement

- context.routes.ts ka /context endpoint enhance karo

- Naya /context/enhanced endpoint banao:

- recent events fetch karo (last 24 hrs)

- recent braindumps fetch karo

- memoryService.buildContextFromMemory() call karo

- aiService.generateContextSummary() call karo

- stalenessService.getAllScores() merge karo

- POST /ai/reason endpoint banao — Person 3 ka /reconstruct yeh use karega

- GET /memory/query endpoint banao

### Day 5 — Testing & Polish

- /context/enhanced ka full test karo real data se

- AI summary quality check karo — prompt tune karo

- POST /ai/reason response format verify karo: { summary, confidence, next_steps }

- Error handling add karo — agar AI API down ho toh fallback

👤 Person 3 — Product Layer Files: sessionService.ts, session.routes.ts, dashboard.routes.ts, dashboard UI, reconstruct.routes.ts ¦ Est: 5 Days

## 3.3  Person 3 — Day-by-Day Tasks

### Day 1 — Planning & Mock Setup

- Technical document padho — apne saare files samjho

- Dashboard HTML structure likho (mock data se — real API baad mein lagegi)

- Dashboard mein kya dikhana hai decide karo: events count, active session, top files, staleness

- Chart.js CDN se simple bar/line chart prototype banao

- Git pull — Person 1 ka db.ts Day 1 end tak ready hoga

Day 1 par Person 3 ko DB ki zarurat nahi. Dashboard UI mock data se parallel shuru karo. Sessions ka real kaam Day 2 se.

### Day 2-3 — Session Service & API

- git pull — db.ts mein sessions table ready mil jayegi

- sessionService.ts create karo:

- startSession(project?) → sessionId — sessions table mein insert karo

- endSession(sessionId) → summary generate karo (events count, files touched)

- getCurrentSession() → active session return karo

- getSessionHistory(limit) → past sessions list

- session.routes.ts implement karo — stub se real logic

- POST /session/start aur POST /session/end properly implement karo

- GET /session/current aur GET /session/history add karo

### Day 3-4 — Dashboard Backend + UI Connect

- dashboard.routes.ts create karo:

- GET /dashboard/stats → { totalEvents, totalBrainDumps, activeSessions, topFiles }

- GET /dashboard/timeline?hours=24 → hourly event counts

- Dashboard UI ko real API se connect karo (mock data replace karo)

- Fetch calls: /dashboard/stats, /dashboard/timeline, /session/history, /staleness/all

- Auto-refresh every 30 seconds add karo

- Responsive design check karo

### Day 5 — Reconstruct API + Status Bar

- Person 2 ka /ai/reason endpoint ab ready hoga — use karo

- reconstruct.routes.ts implement karo:

- GET /reconstruct/:projectId → memory fetch karo, /ai/reason call karo

- Response: { projectId, brief, confidence, next_steps }

- VS Code status bar (statusBar.ts) banana optional hai — agar time ho

- Full dashboard test karo real data se

# 4. Daily Coordination Checklist

Har din subah 10 min standup — sirf teen sawaal: kya kiya, kya karoge, koi blocker?

| Day 1 | Person 1 – Capture | Person 2 – Intelligence | Person 3 – Product |
| --- | --- | --- | --- |
|  | ☐ db.ts mein 3 naye tables add karo ☐ server.ts mein placeholder routes ☐ Git push — end of day MUST | ☐ Anthropic API key setup karo ☐ aiService.ts skeleton banao ☐ Claude API test message bhejo | ☐ Document padho — apna scope samjho ☐ Dashboard HTML mock banao ☐ Chart.js prototype test karo |

| Day 2 | Person 1 – Capture | Person 2 – Intelligence | Person 3 – Product |
| --- | --- | --- | --- |
|  | ☐ wsServer.ts — terminal events add ☐ extension.ts — terminal capture ☐ Person 2 aur 3 ko db.ts confirm karo | ☐ git pull — db.ts le lo ☐ memoryService.ts — saveNode, query ☐ stalenessService.ts — updateScore | ☐ git pull — db.ts le lo ☐ sessionService.ts — startSession ☐ session.routes.ts — start/end implement |

| Day 3 | Person 1 – Capture | Person 2 – Intelligence | Person 3 – Product |
| --- | --- | --- | --- |
|  | ☐ extension.ts — git commit capture ☐ wsServer.ts — staleness update call ☐ Unit test: saare event types | ☐ memoryService — buildContextFromMemory ☐ stalenessService — getAllScores ☐ Test: memory nodes insert/query | ☐ sessionService — history, current ☐ dashboard.routes.ts — stats endpoint ☐ Dashboard UI — real API connect shuru |

| Day 4 | Person 1 – Capture | Person 2 – Intelligence | Person 3 – Product |
| --- | --- | --- | --- |
|  | ☐ End-to-end flow test karo ☐ Person 2 ki /context/enhanced test karo ☐ Bug fixes report karo | ☐ context.routes.ts — /context/enhanced ☐ POST /ai/reason endpoint ☐ GET /memory/query endpoint | ☐ dashboard/timeline endpoint ☐ Dashboard charts — live data ☐ Auto-refresh implement karo |

| Day 5 | Person 1 – Capture | Person 2 – Intelligence | Person 3 – Product |
| --- | --- | --- | --- |
|  | ☐ Person 3 ke dashboard API test karo ☐ Extension flow full test ☐ Performance check | ☐ /context/enhanced quality test ☐ AI prompt tune karo ☐ Error handling — AI API fallback | ☐ reconstruct.routes.ts — AI call ☐ Dashboard final polish ☐ Session lifecycle full test |

| Day 6-7 | Person 1 – Capture | Person 2 – Intelligence | Person 3 – Product |
| --- | --- | --- | --- |
|  | ☐ Full integration test ☐ Bugs fix karo ☐ README update | ☐ Integration test support ☐ Memory/AI edge cases fix ☐ Performance optimize | ☐ Dashboard final UI polish ☐ Cross-browser test ☐ Demo script prepare |

# 5. Inter-person Dependency Map

Yeh table clearly dikhata hai kaun kisko block kar sakta hai, aur handoff kaise hogi.

| Task / File | Blocks Whom | Blocked By | Handoff Format |
| --- | --- | --- | --- |
| P1: db.ts (Day 1) | P2 (memory), P3 (session) | None — starts Day 1 | git push — schema SQL + running DB |
| P1: server.ts routes | P2, P3 (mount points) | None | git push — route file placeholders |
| P2: aiService.ts | P3 (reconstruct uses /ai/reason) | P1 db.ts (for context) | API endpoint live on localhost:3001 |
| P2: memoryService.ts | P2 own (context/enhanced needs it) | P1 db.ts schema | npm module import + tested |
| P2: stalenessService.ts | P3 (dashboard shows staleness) | P1 wsServer update | GET /staleness/all live |
| P2: /context/enhanced | P3 (reconstruct calls this) | P2 ai + memory + staleness | Documented response format |
| P3: sessionService.ts | P3 own (dashboard, reconstruct) | P1 db.ts sessions table | Session CRUD tested |
| P3: dashboard.routes.ts | No one else blocks | P1 db, P2 staleness/memory | GET /dashboard/stats live |
| P3: /reconstruct/:id | Final product feature | P2 /ai/reason endpoint | Full response with AI brief |

## 5.1 Critical Path (Longest Blocking Chain)

Person 1 → db.ts complete (Day 1 EOD) ↓ Person 2 → memoryService + stalenessService + aiService (Day 2-4) ↓ Person 2 → /context/enhanced + /ai/reason ready (Day 4 EOD) ↓ Person 3 → /reconstruct/:projectId implement (Day 5) ↓ All → Integration testing (Day 6-7) Total critical path: 7 days — matches sprint duration exactly. Agar Person 2 delay ho jaye, Person 3 ka reconstruct feature delay hoga.

## 5.2 What Can Run 100% Parallel (No Dependency)

| Person 2 can do in parallel with Person 3 | Person 3 can do without waiting for anyone |
| --- | --- |
| ✓ aiService.ts Day 1 se ✓ memoryService.ts after db.ts git push ✓ stalenessService.ts independently | ✓ Dashboard HTML/UI Day 1 se (mock data) ✓ sessionService.ts after db.ts push ✓ dashboard.routes.ts independently |

# 6. Three Mandatory Sync Points

Sirf yeh 3 baar teeno logon ko ek saath milna hai. Baaki time independent kaam.

🔵 SYNC POINT 1 — Day 1 Evening (30 min) Trigger: Person 1 ka db.ts complete hone ke baad Person 1 share karta hai: • db.ts ka final schema (git push karo) • Server running hai — localhost:3001/health confirm karo • Tables create confirm: sessions, memory_nodes, staleness_scores Person 2 + 3 verify karte hain: • git pull karo aur db.ts dekho • npm run dev — server start hota hai confirm karo

🟢 SYNC POINT 2 — Day 4 Evening (45 min) Trigger: Person 2 ka /ai/reason aur /context/enhanced ready hone ke baad Person 2 share karta hai: • POST /ai/reason — request/response demo karo • GET /context/enhanced — live response dikho • GET /staleness/all — Person 3 ke dashboard ko data milega yahan se Person 3 confirm karta hai: • Dashboard mein /staleness/all se data aata hai • /reconstruct mein /ai/reason ko call karne ka plan confirm karo

🟣 SYNC POINT 3 — Day 6 Morning (2 hours) Full Integration Test — Teeno saath kaam karte hain Test scenarios (ek-ek karke): 1. Extension se file change karo → DB mein event dikhna chahiye → dashboard timeline update ho 2. Brain dump add karo → memory_nodes mein store ho → /context/enhanced mein aaye 3. Session start karo → kuch files edit karo → session end karo → history mein dikhe 4. /reconstruct/testProject call karo → AI brief return honi chahiye 5. Dashboard open karo → live stats, timeline, staleness scores dikhne chahiye

# 7. Risk Register & Mitigation Plan

| Risk | Severity | Affects | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Person 1 db.ts delay ho jaye | HIGH | P2 + P3 both | P2 apna mock DB use kare temporarily, P3 Day 1 UI pe focus kare | Person 1 |
| Anthropic API key nahi mila | HIGH | P2 fully | Day 1 hi key manage karo; fallback: OpenAI ya simple rule-based summary | Person 2 |
| AI API rate limit / cost | MED | P2 features | Cache responses, test ke liye mock return use karo, production mein real call | Person 2 |
| Person 2 aur 3 DB conflict | MED | P2 + P3 | db.ts ek hi jagah hai, Person 1 maintain kare, baki sirf read kare | Person 1 |
| Dashboard CORS issue | MED | P3 dashboard | server.ts mein already CORS hai; check karo localhost:5500 allowed hai | Person 3 |
| /reconstruct waqt pe na bane | LOW | P3 Day 5 task | Yeh stretch goal hai — baaki sab done hone ke baad implement karo | Person 3 |
| Extension WebSocket drop | LOW | P1 events | wsServer mein reconnect logic add karo — simple setTimeout retry | Person 1 |

# 8. Team Communication Protocol

## 8.1 Daily Standup Format (10 min, subah)

Har person 3 sawaalon ke jawab deta hai: 1. Kal kya kiya? (1-2 sentences) 2. Aaj kya karunga? (1-2 sentences) 3. Koi blocker hai? (haan/nahi — agar haan toh turant resolve karo) If blocker hai: 15 min extra call teeno ke beech, baaki kaam rok ke.

## 8.2 Git Workflow

- Branch naming: p1/db-schema, p2/ai-service, p3/session-service

- Main branch mein push sirf working code — broken code push mat karo

- Jab koi shared file (db.ts, server.ts) change karo → turant team ko WhatsApp/Slack pe batao

- Daily EOD: apna kaam push karo — dusre loge pull karenge subah

## 8.3 Shared Contracts (Change Mat Karo Bina Pooche)

Yeh interfaces FIXED hain. Bina team consent ke change mat karo: 1. DB Schema (db.ts tables) — Person 1 maintains, others only read 2. POST /ai/reason response: { summary: string, confidence: number, next_steps: string[] } 3. WebSocket message format: { type: string, filePath?: string, ts: number } 4. GET /staleness/all response: [ { filePath: string, score: number, lastSeen: number } ] Agar change zaruri lage: team mein discuss karo pehle.

# 9. Definition of Done — Sprint Complete Checklist

Yeh sab check hona chahiye Day 7 tak:

|  | Person 1 ☐ db.ts — 5 tables working ☐ WebSocket — 3 event types handle ☐ Extension — terminal + git capture ☐ server.ts — all routes mounted |  | Person 2 ☐ /ai/reason — real Claude response ☐ /memory/query — project data return ☐ /staleness/all — scored list return ☐ /context/enhanced — AI + memory + staleness |  |
| --- | --- | --- | --- | --- |
|  | Person 3 ☐ Session start/end/history working ☐ Dashboard — live data dikhta hai ☐ /reconstruct — AI brief return ☐ Dashboard auto-refresh working |  | All Together ☐ File change → dashboard update ☐ Brain dump → AI context mein aaye ☐ Session full lifecycle test ☐ /reconstruct — end-to-end demo ready |  |

Sprint ends Day 7 — Demo ready. Ship it. 🚀